## October 2025 Timesheet
Date | Day | Focus Area / Task Description | Detailed Activities | Time Spent (hrs) | Deliverables
01-10-25 | Wednesday | TruffleHog API Planning & Database Schema Design | Analyzed scanning requirements, designed MongoDB schema, planned API endpoints. | 2 | Database schema, API spec
02-10-25 | Thursday | TruffleHog Results & Stats APIs | Developed results and stats endpoints, implemented filtering and pagination. | 2 | Results & Stats APIs
03-10-25 | Friday | Critical Findings & Secret Types APIs | Built critical findings and secret-type endpoints, added risk scoring. | 2 | Critical & Secret-Type APIs
04-10-25 | Saturday | CSV Export & Executive Summary APIs | Developed CSV export and executive summary APIs with large dataset handling. | 2 | CSV & Summary APIs
07-10-25 | Monday | Detailed Report API & Testing | Implemented detailed report API, performed validation and bug fixes. | 2 | Detailed Report API
08-10-25 | Wednesday | Queue API Planning & Architecture | Designed TruffleHog queue system and RabbitMQ integration. | 2 | Queue architecture design
09-10-25 | Thursday | RabbitMQ Docker Configuration | Configured RabbitMQ in docker-compose, setup ports and credentials. | 2 | RabbitMQ docker setup
10-10-25 | Friday | Queue Management APIs - Add & Trigger | Created endpoints for adding and triggering repository scans. | 2 | Add & Trigger APIs
11-10-25 | Saturday | Queue Status API & Monitoring | Implemented status API for queue monitoring and metrics retrieval. | 2 | Queue status API
14-10-25 | Monday | Automation Scripts & Testing Infrastructure | Created setup and test automation scripts, validated services. | 3 | Automation scripts
15-10-25 | Tuesday | Docker Image Building & Deployment | Executed setup scripts, built and tested docker images. | 2 | Docker images built
16-10-25 | Wednesday | Port Conflicts & Service Configuration | Resolved port conflicts, debugged RabbitMQ startup errors. | 2 | Port conflicts resolved
17-10-25 | Thursday | RabbitMQ Cookie Configuration & Container Issues | Added cookie configuration, tested containers and permissions. | 2 | Config tests, issue logs
18-10-25 | Friday | Integration Testing & Error Handling | Performed integration testing and fixed issues across APIs. | 3 | Integration test results
21-10-25 | Monday | System Reboot & Clean Deployment | Rebooted and redeployed containers, verified all services. | 2 | Clean deployment
22-10-25 | Tuesday | MongoDB Connection Debugging | Fixed hardcoded DB connections, verified container connectivity. | 2 | Connection fix plan
23-10-25 | Wednesday | API Enhancement & Script Testing | Improved API validation, tested automation scripts. | 2 | Enhanced APIs & scripts
24-10-25 | Thursday | RabbitMQ Health Verification & Testing | Verified RabbitMQ health and tested management UI. | 2 | Health verification report
25-10-25 | Friday | Backend Services Analysis & Integration Testing | Analyzed backend MongoDB connections and validated integration. | 2 | Integration validation
28-10-25 | Monday | Final Status Verification & Timesheet Preparation | Validated services, verified health status, prepared documentation. | 3 | Final report & timesheet